## Sheet1
Backlog item ID	Backlog item story	Story	Task owner	Initial estimate	Week 1	Week 2	Week 3
1	As a user I want to create an account	design user interface	Thibault	2	0	0	2
		implement back-end code	Thibault	4	2	1	1
		implement front-end code	Thibault	3	1	2	0
		complete unit testing	Thibault	1	0	0	1
		write documentation	Thibault	1	0	0	1
1	As a user I want to logint	design user interface	Thibault	2	0	0	2
		implement back-end code	Thibault	3	2	1	0
		implement front-end code	Thibault	2	1	1	0
		complete unit testing	Thibault	1	0	0	1
		write documentation	Thibault	1	0	0	1
1	As a user I want to logout	design user interface	Thibault	0	0	0	0
		implement back-end code	Thibault	1	1	0	0
		implement front-end code	Thibault	1	1	0	0
		complete unit testing	Thibault	1	0	0	1
		write documentation	Thibault	1	0	0	1
1	As a user I want to delete an account	design user interface	Thibault	1	0	0	1
		implement back-end code	Thibault	2	0	2	0
		implement front-end code	Thibault	2	2	1	0
		complete unit testing	Thibault	1	0	0	1
		write documentation	Thibault	1	0	0	1